## Instructions
JOIDES RESOLUTION SCIENCE OPERATOR
CORING TIME ESTIMATOR
The JRSO Coring Time Estimator is provided to assist prospective ocean drilling proponents in estimating the time required to complete various common coring options. This is a gross time estimator, and we advise contacting the JRSO Operations Support section for more complex operations (http://iodp.tamu.edu/staffdir/tamu_sciops.html#op)
(1) The worksheet provides a simple method for estimating gross drilling times and transit times for general planning purposes.
The "Coring Time" worksheet provides a method to calculate coring times. There are now 3 example Coring Time worksheets to illustrate the caculations for a single RCB hole, for 2 holes with APC/XCB + RCB, and for three holes with APC/XCB in two and RCB coring in the third.
The "Transit Time" worksheet provides a method to calculate great circle distances and transit times. However, Google Earth may be a more effective method to plan and estimate transit routing using the Ruler Tool. Assume a transit speed for the JR of 10.5 nautical miles/hour.
The "Summary" worksheet can be used to manually combine transit and site times into an expedition time estimate.
(2) The worksheets are color coded:
Yellow cells are for data entry.
Blue cells are calculated answers based on the embedded formulas.
Default numbers are provided for convenience and can be changed as required.
(3) A typical IODP riserless expedition generally has a 5 day port call and 56 days of operations (transit and on site operations)
(4) The "Coring Time" work sheet has a typical 3 hole site in sediments followed by a typical hard rock penetration.
a) It is advisable to enter "0" in unwanted activities initially (rather than erase them) due to embedded
formulas.
(5) The Advanced Piston Corer (APC) is used in soft to firm sediments and generally penetrates to a depth of about 200 to 300 meters:
a) Hard layers, nodules, or sand can stop APC penetration.
b) APC cores are generally oriented (for paleomagnetic studies) after the third core (0.17 hours/run).
c) Formation temperature measurements using the APTC3 (in APC cutting shoe) are usually taken (to establish a geothermal gradient for hydrocarbon safety purposes) on the fourth core and every third core thereafter (0.3 hours/run) for a minimum of 3 measurements
d) Sediment temperature measurements may be taken as requested using the SET tool when the APCT3 cannot be used (1-1.5 hours/run).
e) APC coring refusal is defined when the APC cannot penetrate the formation or cannot be pulled from the formation.
APC coring depth can be extended beyond APC refusal, if desired, by drilling over stuck core barrels or switching to the half-length APC, (HLAPC).
which takes 4.7 m cores requiring twice the wireline time as the standard APC
(6) The Extended Core Barrel (XCB) is run after APC refusal is reached to core in firm to hard sediments, hard layers, nodules, sand, and mixed hard/soft intervals to a depth of 400 to 800 meters.
a) The APC and XCB systems use the same bottom hole assembly (BHA); therefore, no pipe trip is required.
b) The XCB coring system requires both wireline time and rotating time to cut the core
c) The rotating time with the XCB shoe typically has a penetration rate that decreases from 30 to 12 meters/hour as the formations become harder with depth.
d) XCB coring is terminated when the rate of penetration slows to unacceptable rates or cutting shoes are being damaged.
e) The XCB usually can penetrate pillow basalts to a depth of 20 to 30 meters if required.
(7) The Rotary Core Barrel (RCB) system is used to core in lithified sedimentary rock and basement rocks.
a) After APC/XCB coring operations are concluded, a pipe trip is required to change the BHA.
b) The RCB system can core the hardest rocks and several types of bits are available.
c) The rate of penetration in hard sediments is typically 20 to 9 meters/hour depending on the formation.
d) The rate of penetration in basalts is typically 2.0-4.5 meters/hour
(8) Logs typically require about 18 hours for 600 meter holes, 24 hours for 1000 meter holes, and 36 hours | 33.3333 | 12
for holes deeper than 1500 meters. Check shot surveys (VSI tool) are only conducted during dailight hours and thus are typically 12 hrs maximum.
(9) Reentry cones and casing may be required in unstable formations or for long term observatories or for penetrations deeper than ~1300 meters in sediments (200 meters in basement). Please contact the Operations Support section for assistance.

## Coring-Logging Time
| CORING TIME ESTIMATES |  |  |  | 2026-08-06 12:29 | 46240.5204
Yellow cells are for data entry
Blue cells are calculated answers based on embedded formulas.
1) Default values can be changed. Enter "0" to cancel operation.
2) Choose from the several common coring scenarios listed.
3) Refer to the guidelines below for common coring performance ranges.
| EXPEDITION | XXYYZZ
| SITE: | AABB-1A
| WATER DEPTH: | 1800 | Meters
APC/XCB CORE 3 HOLES, NO LOGS
Hole A
ACTION | PENETRATION | TIME | CORES | TIME/RT | PEN RATE
| (meters) | (hours) | (number) | (hours) | (meter/hr)
Survey & Loc Site: |  | 1
Trip In: | 1800 | 5.1579
APC To: | 250 | 20.8 | 26 | 0.8
Orient: |  | 4.08 | 24 | 0.17
APCT3 Heat flow: |  | 1.2 | 4 | 0.3
SET: |  | 0 | 0 | 1
Zone 1, XCB To: |  | 0 | 0 | 0 | 12
Zone 2, XCB To: |  | 0 | 0 | 0 | 2
Pull up to Sea Floor: | 250 | 0.4386
-----------
| Hole A= | 32.6765 | Hours= | 1.3615 | Days
Hole B
ACTION | PENETRATION | TIME | CORES | TIME/RT | PEN RATE
| (meters) | (hours) | (number) | (hours) | (meter/hr)
Move & Spaceout: | 0 | 1
Trip In: | 0 | 0
APC To: | 250 | 20.8 | 26 | 0.8
Orient: |  | 4.08 | 24 | 0.17
Zone 1, XCB To: | 0 | 0 | 0 | 0 | 12
Zone 2, XCB To: | 0 | 0 | 0 | 0 | 2
Pull up to Sea Floor: | 250 | 0.4386
----------
| Hole B= | 26.3186 | Hours= | 1.0966 | Days
Hole C
ACTION | PENETRATION | TIME | CORES | TIME/RT | PEN RATE
| (meters) | (hours) | (number) | (hours) | (meter/hr)
Move & Spaceout: |  | 1
APC To: | 250 | 20.8 | 26 | 0.8
Zone 1, XCB To: | 500 | 34.3333 | 26 | 1 | 30
Zone 2, XCB To: | 700 | 31 | 21 | 1 | 20
Treat Hole: |  | 0
Logging: |  | 0
Trip out to Ship: | 2500 | 6.386
-----------
| Hole C= | 93.5193 | Hours= | 3.8966 | Days
DRILL TO APC/XCB REFUSAL, RCB CORE & LOG
Hole D
ACTION | PENETRATION | TIME | CORES | TIME/RT | PEN RATE
| (meters) | (hours) | (number) | (hours) | (meter/hr)
Trip In: | 1800 | 5.6
Drill To: | 700 | 28.9333 |  |  | 30
Zone 1, RCB To: | 900 | 33.4667 | 21 | 0.8 | 12
Zone 2, RCB To: | 1000 | 23.5 | 10 | 1.1 | 8
Zone 3, RCB To: | 1100 | 44.3333 | 10 | 1.1 | 3
Zone 4, RCB To: | 0 | 0 | 0 | 0 | 3
Trip for Bit: |  | 0 | 0 | 14.7
Treat Hole,Drop Bit: |  | 8
Logging: |  | 34 | 1.3333
Trip Out to Ship: | 1900 | 5.3333
-
| Hole D= | 183.1667 | Hours= | 7.6319 | Days
-
| Site (Holes A-D)= | 335.6811 | Hours= | 13.9867 | Days

## Transit Time
GREAT CIRCLE DISTANCE
|  | PROPOSAL |  |  | 2-Full
Walvis Ridge
Yellow cells are for data entry.
Blue cells are calculated answers based on embedded formulas.
1) Enter ship speed (default value is 10.5 knots for transits).
2) Enter latitude and longitude (format may be degrees or decimals).
North and West are positive values.
South and East are negative values (both degrees and minutes are negative).
3) Data can be copied to a lower cell.
Travel Time between coordinate points is based on a speed of:
| >>>>> | 10.5 |  | KNOTS = nmi/hr <<<<<
| INITIAL POINT |  |  | FINAL POINT |  |  | MILES |  | TIME | TIME
| [deg.] | [min.] |  | [deg.] | [min.] |  | [nmi] |  | [hours] | [days]
| Cape Town |  |  | AABB-1A
[7 empty] | [nmi] |  | [hours] | [days]
LAT | -33.93 |  | -0.59219 | -32.6489 |  | -0.56983 | 922.9505 | 0.26848 | 87.9 | 3.6625
LONG | 18.42 |  | 0.32149 | 0.05707 |  | 0.00099606
| AABB-1A |  |  | CCDD-2B
[7 empty] | [nmi] |  | [hours] | [days]
LAT | -32.6489 |  | -0.56983 | -30.3807 |  | -0.53024 | 145.9698 | 0.042461 | 13.9019 | 0.57925
LONG | 0.05707 |  | 0.00099606 | 1.0893 |  | 0.019013
[7 empty] | [nmi] |  | [hours] | [days]
LAT | [5 empty] | 0 | 0 | 0 | 0 | 0
LONG | [5 empty] | 0
[7 empty] | [nmi] |  | [hours] | [days]
LAT | [5 empty] | 0 | 0 | 0 | 0 | 0
LONG | [5 empty] | 0
[7 empty] | [nmi] |  | [hours] | [days]
LAT | [5 empty] | 0 | 0 | 0 | 0 | 0
LONG | [5 empty] | 0
[7 empty] | [nmi] |  | [hours] | [days]
LAT |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
LONG |  |  |  |  | 0 | 0
[7 empty] | [nmi] |  | [hours] | [days]
LAT | [5 empty] | 0 | 0 | 0 | 0 | 0
LONG | [5 empty] | 0
[7 empty] | [nmi] |  | [hours] | [days]
LAT | [5 empty] | 0 | 0 | 0 | 0 | 0
LONG | [5 empty] | 0
[7 empty] | [nmi] |  | [hours] | [days]
LAT | [5 empty] | 0 | 0 | 0 | 0 | 0
LONG | [5 empty] | 0
[7 empty] | [nmi] |  | [hours] | [days]
LAT | [5 empty] | 0 | 0 | 0 | 0 | 0
LONG | [5 empty] | 0

## Summary
|  | Water |  | Transit | Coring | Log | Total
Site | Latitude N | Depth | Operations | 10.5 kt | Time
Name | Longitude W | (m) | (mbsf) | (days) | (days) | (days) | (days)
Expediton XXX, Port Call in Cape Town | [6 empty] | 5
Transit from Cape Town to Site AABB-1A: |  |  |  | 3.66 |  |  | 3.66
AABB-1A | 32.64889°S | 1800 | Hole A: APC to 250 mbsf |  | 1.4 |  | 1.4
| 0.05707°E |  | Hole B: APC to 250 mbsf |  | 1.1 |  | 1.1
|  |  | Hole C: APC to 250 mbsf, XCB to refusal |  | 3.9 |  | 3.9
|  |  | Hole D: Drill without coring to XCB depth, RCB to 1100 m, Log w/ Triple Combo, FMS-sonic |  | 6.3 | 1.3 | 7.6
14
Transit from last site to end port
|  |  | Est Time= | 3.66 | 12.7 | 1.3 | 17.66
|  |  | Available Time = |  |  |  | 61
ALTERNATE SITES
|  | Water |  | Transit | Coring | Log | Total
Site | Latitude N | Depth | Operations | 10.5 kt | Time
Name | Longitude W | (m) | (mbsf) | (days) | (days) | (days) | (days)